## Start here
Apparel ERP Implementation Checklist — by MerchandiserOS
A free, vendor-neutral working file for putting an ERP (Odoo, NetSuite, SAP, Dynamics 365 or any other) into a textile or apparel business.
WHAT THIS IS
A checklist to test whether an ERP really fits how a garment, knit, hosiery or textile business works — style/colour/size grids, fabric by weight and length, dye lots, seconds, subcontract work, AQL inspection and letters of credit.
It is written for ERP consultants and for factory owners and managers. It does not favour any ERP vendor.
HOW TO USE IT
1. Start with “Fit-gap (52)”. For each requirement, mark how important it is to you (Must / Should / Could).
2. Ask the ERP partner to show each line working on your own data, then mark the Fit column (see legend below). Do not accept a slide as proof.
3. Write in “How it will be met” exactly what will be set up or built, and name one Owner per line.
4. Use “Decisions before go-live” to record the choices that are expensive to change later — item model, costing, units, BOM, lots, work-order level.
5. Before go-live, run every line in “Test scenarios (13)” from start to finish with real styles. A scenario only passes when the finance result is right too.
6. Work through “Go-live checklist” in the final weeks, and use “Who owns what” to agree which system holds the master copy of each piece of data.
7. Pale yellow cells are for you to fill in. Cells with a small arrow have a drop-down list.
8. Filter any sheet by Area or Owner using the arrows in the header row.
LEGEND — FIT COLUMN
Standard | Works out of the box. No set-up beyond normal data entry.
Configure | Possible with settings, fields, workflows or reports — no programming.
Custom build | Needs programming or a paid add-on. Record the cost and who maintains it after upgrades.
Operations layer | Handled in a specialist system alongside the ERP (for example PLM, shop-floor capture, or an operations layer such as MerchandiserOS), which passes the result to the ERP.
Not needed | Does not apply to this business (for example EDI for a factory with no retail buyers).
LEGEND — PRIORITY
Must | Go-live cannot happen without it.
Should | Needed soon after go-live; a short workaround is acceptable.
Could | Nice to have; plan for a later phase.
EXAMPLE ROW
Line 21 “Record GSM and cuttable width per lot or roll” — Priority: Must · Fit: Configure · How it will be met: two extra fields on the lot record, filled at receiving from the supplier’s packing list · Owner: Stores manager.
Full guide | Full guide: https://www.merchandiseros.online/erp-guide
Licence | Published by MerchandiserOS — free to use and share with attribution.
Last updated | 26 Sep 2026
Note | General practitioner guidance, not a guarantee of any product’s capability. Check country-specific rules (for example e-invoicing) with a local adviser.

## Fit-gap (52)
# | Area | Requirement | Why it matters in apparel | Must / Should / Could | Fit | How it will be met | Owner | Notes
1 | Product | Hold one style master with a colour × size (and fit/length where used) variant matrix, rolled up to style level. | One style can mean 100+ SKUs; treating each as a separate item makes reporting and ordering by style impossible.
2 | Product | Define size scales per product category (e.g. XS–XXL, waist/inseam, shoe-size bands for socks). | Different categories use different size runs; one global size list produces wrong grids and wrong orders.
3 | Product | Record the season or collection on each style, and allow the same style number to be reused across seasons. | Without a season attribute, last season’s cost, BOM or supplier is silently used for this season’s order.
4 | Product | Carry a style over to a new season with its own price, BOM and supplier, keeping history of the old one. | Carry-over styles are common; overwriting them destroys the cost history needed for the next quote.
5 | Product | Support prepacks and ratio packs (e.g. 1S:2M:2L:1XL) as a sellable unit made up of pieces. | Buyers order packs, the floor makes pieces and the warehouse holds cartons — three units on one order line.
6 | Product | Support pairs and multi-packs (hosiery, gloves) with correct units for making, stocking and selling. | Singles are knitted, paired, then packed; counting in the wrong unit distorts yield and wastage.
7 | Product | Store each buyer’s own style and colour codes against our style and colour. | Buyer documents, labels and ASNs must quote the buyer’s codes, not the factory’s.
8 | Product | Link each style to its tech-pack revision, so everyone knows which version is current. | When the spec lives outside the system with no revision link, production runs on a superseded spec.
9 | Product | Hold points of measure (POM) with tolerances per size. | Measurement checks and buyer approvals depend on per-size specs and tolerances.
10 | Product | Track sample types and rounds (proto, fit, size set, PP, TOP) with comments and an approval decision. | Bulk production normally waits on sample approvals; tracking them as sales orders hides the real status.
11 | BOM & costing | Apply BOM rules by colour and size within one style BOM (e.g. thread and zip change with colour). | One BOM per SKU duplicates everything; one BOM per style loses colour-specific trims.
12 | BOM & costing | Use size-graded fabric consumption instead of one average. | Average consumption leaves large sizes short of fabric.
13 | BOM & costing | Record wastage and shrinkage as separate allowances. | Shrinkage is a spec property and wastage is a process loss; mixing them hides where material is lost.
14 | BOM & costing | Hold trims that change by colourway (labels, thread, buttons). | Wrong-colour trims are a common cause of line stoppages and rework.
15 | BOM & costing | Pre-cost a quote with several elements (fabric, trim, CM, wash, testing, freight, finance, commission) and exchange rates. | Quotes are built this way; a single cost figure cannot be checked or compared later.
16 | BOM & costing | Compare standard cost with actual cost per order and show the variance. | Without a pre-cost → standard → actual link, a loss-making order looks profitable until year end.
17 | BOM & costing | Cost labour as CM (cut-make) based on SMV (standard minutes). | Labour is usually costed from standard minutes; a fixed labour rate per item is not how factories quote.
18 | BOM & costing | Spread landed cost (freight, duty, clearing, bank charges) onto material receipts. | If landed cost is expensed rather than added to stock, garment cost is understated.
19 | BOM & costing | Keep versions of a quote with an approval step. | Buyers renegotiate; the agreed version must be the one that drives the order and the cost.
20 | Materials & inventory | Use separate purchase, stock and issue units per material, with a conversion that can differ by lot. | Knit fabric is bought in kg and cut in metres; a fixed conversion is wrong because it varies by roll.
21 | Materials & inventory | Record GSM and cuttable width per lot or roll. | Metres per kg = 1000 ÷ (GSM × width in m), so these two values are needed to convert correctly.
22 | Materials & inventory | Track fabric roll by roll (length, width, GSM, shade, defects, location). | Cutting plans and claims to suppliers are made per roll, not per lot total.
23 | Materials & inventory | Track dye lot and shade band, and allocate so one garment is cut within one shade. | Mixing shades in a garment causes visible panel differences and rejected lots.
24 | Materials & inventory | Record 4-point fabric inspection results per roll. | Inspection results decide whether fabric is accepted, claimed or used for less visible parts.
25 | Materials & inventory | Hold material in a QC / quarantine status until it passes inspection. | Uninspected fabric issued to cutting turns a supplier problem into a garment problem.
26 | Materials & inventory | Record consigned (buyer-supplied) stock as not owned, in its own location. | In CMT work the fabric belongs to the buyer; recording it as purchased stock overstates assets.
27 | Materials & inventory | Separate stock reserved for an order from free stock. | Without reservations, material bought for one order is quietly used on another.
28 | Materials & inventory | Handle leftovers and stock-lot disposal (sale or write-off). | Leftover fabric and trims build up after every season and need a clear value and exit route.
29 | Production | Create work orders at the chosen level (style-colour, delivery or cut). | The work-order level decides how WIP, material issue and output can be reported.
30 | Production | Plan cut orders and lay plans, and record marker efficiency. | Marker efficiency drives actual fabric use, and so actual cost.
31 | Production | Create bundles and bundle tickets for tracking through sewing. | Bundle tickets are how most sewing floors track pieces, sizes and shades.
32 | Production | Show WIP by stage and by line. | Management needs to see where each order is on the floor, not only what has finished.
33 | Production | Grade output as A-grade, B-grade/seconds, repairs and rejects. | If every unit counts as saleable, “produced” overstates what can actually ship.
34 | Production | Send work out to subcontractors (embroidery, print, wash, dye) and receive it back with an allowed loss. | If out and return are not linked, pieces at subcontractors and process losses become invisible.
35 | Production | Plan capacity by line using SMV. | Booking orders without checking line capacity is how ship dates are missed.
36 | Production | Run a T&A (time and action) calendar with a critical path back from the ex-factory date. | Without it, the T&A stays in Excel and late milestones are found too late.
37 | Quality | Capture inline and end-of-line inspection results. | Defects caught inline are far cheaper to fix than at final inspection.
38 | Quality | Run final AQL inspection to ISO 2859-1 using the buyer’s sampling plan. | Buyers set the AQL levels (commonly 2.5 major / 4.0 minor); ship release depends on the result.
39 | Quality | Allow a failed inspection to be overridden only by a named person, with the reason logged. | Silent overrides remove the evidence needed when a buyer later claims against the shipment.
40 | Quality | Store lab tests and certificates per order. | Buyers require test reports and certificates before or with shipment.
41 | Sales & shipping | Enter orders as a colour × size grid. | Entering 120 lines one by one is slow and error-prone; buyers send orders as grids.
42 | Sales & shipping | Split one order into several deliveries with their own dates and destinations. | Buyer orders are routinely shipped in several drops to different destinations.
43 | Sales & shipping | Apply over- and under-shipment tolerances per order or buyer. | Shipping outside tolerance can trigger rejection or chargebacks; inside it must still invoice correctly.
44 | Sales & shipping | Pack cartons (including ratio packs) and print carton labels, with SSCC codes where required. | Retail buyers check carton contents and labels against the ASN.
45 | Sales & shipping | Exchange EDI documents where buyers require them (850 order, 855 acknowledgement, 856 ASN, 810 invoice). | Large retailers trade by EDI; manual re-keying causes errors and deductions.
46 | Sales & shipping | Hold each buyer’s label, packing and ASN rules. | Each retailer has its own rules; breaking them leads to chargebacks.
47 | Finance | Handle multiple currencies and month-end FX revaluation. | Sales are often in USD or EUR while costs are in local currency.
48 | Finance | Store letter-of-credit terms and check shipping documents against them before presenting. | Under UCP 600, payment depends on documents matching the LC; discrepancies delay or reduce payment.
49 | Finance | Record customer advances and supplier advances against orders. | Advances are common in apparel and must be matched to the right order.
50 | Finance | Record chargebacks and deductions with a reason code. | Uncoded short payments cannot be disputed or traced back to their cause.
51 | Finance | Report profitability per order and per style. | Owners need to know which buyers and styles make money, not only the monthly total.
52 | Finance | Issue e-invoices in the format each country requires. | Several countries require electronic invoicing; check the local rules with an adviser.

## Decisions before go-live
Decision | Options | Who decides | Decided (Y/N) | Decision taken | Date
Item master & variant model | Style template with generated colour/size variants vs every SKU as its own item; which dimensions (colour, size, fit, length); size scale per category | Merchandising + IT; owner signs off
When variants are created | At design / at costing / at order confirmation (recommended, to avoid a swamp of unused SKUs) | Merchandising + IT
Code convention | Meaningful codes (style-season-colour-size) vs system numbers with descriptions; how buyer codes are held | Merchandising + IT
Season and carry-over rule | Season on the style vs on the variant; carry-over copies style with new price/BOM vs edits the old one | Merchandising
Costing model | Pre-cost (quote) → standard → actual; which stages are used and how they link | Finance + merchandising; owner approves
Cost elements and currency | Fabric, trim, CM, washing, testing, freight, finance cost, commission; costing currency; FX rate source | Finance + merchandising
Costing level and variance | Cost at style or style-colour level; variance buckets (material price, usage, labour, overhead); who approves a cost | Finance
Units of measure | Purchase / stock / issue unit per material; fixed vs per-lot conversion; pieces, pairs, packs, cartons, dozens | Stores, purchasing, production
BOM structure | One style BOM with colour/size rules vs separate BOMs per colourway; size-graded consumption; wastage and shrinkage kept separate | CAD/marker + production
Routing and SMV | Operations and SMV per style; cutting/sewing/finishing stages; subcontract steps as routing operations or separate orders | Industrial engineering + production
Inventory tracking depth | Lot only vs lot + roll; shade attribute mandatory or optional; 4-point inspection per roll; bin locations | Stores + quality
QC status and consigned stock | Quarantine until pass vs issue on receipt; how buyer-supplied (consigned) fabric is recorded; leftover disposal rule | Stores + quality + finance
Work-order level | Work order per style-colour / per delivery / per cut | Production manager + cutting master
WIP capture method | Bundle scans / line-end counts / kiosk entry; who enters it and when | Production manager
Output grading | Grade at output (A / B / repair / reject) and ship readiness counted on A-grade only, or not | Production + quality
Subcontract flow | Out/return documents, allowed loss %, per-piece charging, ownership while away, approved-subcontractor list (buyer compliance) | Production + compliance
Quality / AQL override rule | Default sampling plan (ISO 2859-1, general level II) vs buyer’s plan; who may override a failed inspection and how it is logged | QA manager (buyer QA manual applies)

## Test scenarios (13)
# | Scenario | What to prove | Steps | Expected result | Pass / Fail | Tester | Date
1 | FOB order through to payment | The full cycle works end to end: quote, order, materials, production, inspection, shipment, invoice and payment received. |  | Order closed, stock and WIP at zero for that order, payment matched and order profit reported.
2 | CMT order with buyer-supplied fabric | Consigned fabric is received as not owned, issued, reconciled against garments made, and the invoice is for the service only. |  | Fabric never appears as company stock; balance fabric returned or accounted for; service invoice issued.
3 | Prepack (ratio pack) order | An order in packs drives production in pieces and packing in cartons, with the ASN at pack level. |  | Pieces produced match packs × ratio; carton contents and ASN agree with the order.
4 | Shade split in cutting | Fabric from two shade lots is allocated so each garment is cut within one shade. |  | Cut records show one shade per bundle; no bundle mixes shades.
5 | Subcontract embroidery with loss | Pieces sent out and received back are tracked with a balance, and the allowed loss is recorded. |  | Out, return and loss reconcile; subcontractor charge matches pieces received.
6 | Short shipment within tolerance | An order shipped slightly under quantity, inside the agreed tolerance, is closed and invoiced correctly. |  | Order closes without a false backorder; invoice matches shipped quantity.
7 | Over-shipment | Shipping over the ordered quantity is either blocked or allowed within tolerance, with the right invoice. |  | System applies the tolerance rule; excess handled as agreed with the buyer.
8 | Seconds sale | B-grade output is kept separate from A-grade and sold or written off separately. |  | Seconds never count toward ship readiness; their sale posts to the right account.
9 | LC discrepancy | Shipping documents are checked against stored LC terms and a mismatch is caught before presenting. |  | Discrepancy flagged before documents go to the bank.
10 | Chargeback | A buyer deduction is recorded with a reason code and traced to the shipment that caused it. |  | Deduction posted with reason code and linked to the shipment/ASN.
11 | Mid-season spec revision | A tech-pack change after production has started is visible on the open work order. |  | Work order shows the new revision and the change is flagged to production.
12 | Cancelled order with committed materials | Cancelling an order shows which materials are already bought or issued and what happens to them. |  | Committed materials listed; stock released, reassigned or claimed; cost of cancellation visible.
13 | Foreign-exchange month-end | Open foreign-currency balances are revalued at month end. |  | Revaluation entries post correctly and match the rate used.

## Go-live checklist
Item | Owner | Due | Done (Y/N)
DATA
Open sales orders loaded and checked line by line against the old system
Open purchase orders loaded, with quantities already received deducted
Stock loaded by lot, roll and shade — not as one total per material
Consigned (buyer-supplied) stock loaded separately as not owned
Only active styles migrated; old styles archived, not loaded
Customers and suppliers cleaned: duplicates merged, inactive ones left out
Cut-off rule agreed: which transactions go in the old system and which in the new
Opening balances (customers, suppliers, ledger) reconciled to the old system
Each data owner has signed off their data
PEOPLE
Training done by role, in the local language, using real styles (not demo data)
Floor staff enter data on kiosk or scanner only — no office screens on the floor
Super-users named for each department
Everyone knows who to call on day one
Short how-to sheets available at each workstation and kiosk
SYSTEM
All integrations tested with real data (EDI, bank, PLM, shop floor, carriers)
User permissions set and checked; nobody has more access than their role needs
Approval rules working (cost approval, PO approval, inspection override)
Backups running and a test restore completed
E-invoicing working where the country requires it
Documents and labels print correctly (packing list, carton labels, invoices)
All 13 test scenarios passed
Old system set to read-only after cut-over, and kept for reference
TIMING
Go-live date falls between seasons, not in peak shipping
Parallel run (if any) is short and has a fixed end date
Cut-over rehearsed at least once
Month-end close passed in the new system before hypercare ends
HYPERCARE
Daily issue log set up and reviewed every day
Every issue has a named owner and a target date
Consultants and super-users stay available until the first month-end close
Hypercare exit criteria agreed in advance

## Who owns what
Who owns what — the master copy of each piece of data
Rule of thumb: the ERP is the financial and legal record; specialist systems hold work in progress and the reasoning behind it.
Data object | System of record | Direction | Recommended model
Style, tech pack, POM, spec revision | PLM or operations layer | PLM / ops → ERP on release | Operations layer runs it
SKU (style-colour-size item) | ERP | Created from the released style | Both: defined in the operations layer, item record kept in the ERP
Development BOM | PLM or operations layer | Stays in PLM / ops | Operations layer runs it
Production BOM | ERP | Released from PLM / ops → ERP | Both: built in the operations layer, released to the ERP
Pre-cost (quotation) | PLM or merchandising / operations tool | → ERP as standard cost | Operations layer runs it
Standard and actual cost | ERP | ERP | ERP keeps the record
Customers and suppliers | ERP | ERP → other systems | ERP keeps the record
Sales order / buyer PO | ERP (or EDI → ERP) | ERP → shop floor, T&A | Both: order worked in the operations layer, financial record in the ERP
T&A milestones | Operations tool | Reads ERP events | Operations layer runs it
Material PO, receipts, stock, lots, rolls | ERP (or WMS) | ERP / WMS | Both: procurement planned in the operations layer, stock value in the ERP
Cutting, bundles, WIP, operator output | MES / shop floor | MES → ERP as summaries | Operations layer runs it
Quality results | QMS / MES / operations tool | → ERP as pass/fail that gates shipment | Operations layer runs it
Shipment, ASN, invoice | ERP | ERP → EDI | Both: shipment prepared in the operations layer, invoice issued by the ERP
Payment, letter of credit, chargebacks | ERP | ERP | ERP keeps the record
RECOMMENDED MODEL
One model that works for many factories: an operations layer (for example MerchandiserOS) runs style, quotation, orders, procurement, planning, production, shop floor, quality and logistics, while the ERP keeps the books.
Other set-ups work too — for example a full ERP with a separate PLM and MES. What matters is that every data object has exactly one master.
INTEGRATION RULES
• Link records by the other system’s permanent internal ID, never by a code that people can edit.
• One system writes each field. The other systems read it.
• When two systems disagree, show it to a person as an exception — never overwrite silently.
• Send changes as events where possible, and make every message safe to replay.